## Sheet1
Stand-up questions | Week #1 | Week #2 | Week #3 | Week #4 | Week #5 | Week #6 | Week #7 | Week #8
| 10/8/2022 - 10/15/2022 | 10/16/2022 - 10/22/2022 | 10/22/2022 - 10/28/2022 | 10/28/2022 - 11/04/2022 | 11/04/2022-11/11/2022 | 11/11/2022-11/18/2022 | 11/19/2022-11/25/2022 | 11/26/2021-12/02/2021
Pushya
What tasks did I work on / complete? | understanding the project's requirements creating the UI wireframes for arrival and departure schedules functionality | Devloped UI wireframes for Login page and Home Page, developed UI design for gate assignment | developed the UI and backend for Baggage Carousel | developing the airport employee screen for the website, frontend/backend | displaying baggage carousel number to arriving flights | developing the updated schedule for airline employee frontend | added validations for update schedule | website bug fixes and updated user interface
What am I planning to work on next? | create the basic framework | developing functionalities for airline Employee | developed Enable or disable one or more gates for maintenance | adding validations and displaying data based on selection of inputs for airport employee | displaying baggage carousel summary frontend | developing the updated schedule for airline employee backend | bug fixes and minor UI changes | NA
What tasks are blocked waiting on another team member? | bar: Week #1 to Week #7
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Week #1: we discussed our task progress in the daily meeting and solved any blockers we faced together (XP value: feedback and Simplicity)
Nalini
What tasks did I work on / complete? | Determining entities,attributes along with the relationship | Understanding flow of adding and updating schedule for airline employee DB Design and table creation, mock data for all tables and UI wireframe for login and various roles details page | Developed UI for Home Page frontend and backend | Developed flight schedule page and profile page frontend | updated arrival information for 2 hr and 4 hr | Developed UI and backend implementation for baggage carousel | Developed add schedule for airline employee frontend | Developed backend implementation for the system to prevent conflicting assignments,minor bug fixes and testing the complete flow of the application
What am I planning to work on next? | Table creation and DB design,mock data for all tables | creating wireframe for add schedule page | Developed UI for Login and Signup Page for frontend | updated arrival and departure information based on time | displaying baggage carousel summary frontend | Implementing Required Validations on airline employee | Developed add schedule for airline employee backend | NA
What tasks are blocked waiting on another team member? | bar: Week #1 to Week #8
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Week #1: Through regular meetings, everyone discussed functionalities in details which help us achieved the well reviewed solution.; Week #7: Communication with the team related to integration and testing
Sahithi
What tasks did I work on / complete? | Architecture diagram ,UI wireframe for login page and Home page | Design and creation of tables namely airport, flight, schedules, arrivals, booking, departures, baggage claim in DB and review with the team. | Designed and implemented signin and navigation for home page on frontend | Integrated profile page and flight schedule page on frontend. | updated arrival and departure information for 2 hr and 4 hr | Developed random assignment of gate for arrival and departing flights | Developed add schedule for airline employee frontend | Developed backend implementation for the system to prevent conflicting assignments,minor bug fixes and testing the complete flow of the application
What am I planning to work on next? | DB design | Created UI wireframe for login and airport employee, and airline employee details | Integrated signup and login on backend. | updated arrival and departure information based on time | displaying baggage carousel summary frontend | Developed UI and backend implementation for baggage carousel | Developed updated schedule for airline employee frontend and backend | NA
What tasks are blocked waiting on another team member? | bar: Week #1 to Week #8
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Communication - Discussion about technology stack and requirements | Communication - Discussed about the design decisions with the team and got it reviewed. | Communication - Effectively communicated with the team related toapproach and implementation | Communication - Effectively communicated with the team related toapproach and implementation | Communication - Effectively communicated with the team related toapproach and implementation | Communication - Effectively communicated with the team related toapproach and implementation | Communication with the team related to approach. | Communication with the team related to approach and integrations
Sri thulasi
What tasks did I work on / complete? | Project setup & boilerplate code | Integrated mysql , sign in page mock. | Created customer entities and relationships | Integrated login and signup page on frontend | Added airline employee UI modifications | Merge backend and frontend for airline employee | updated UI for update schedule | Minor bug fixes, hosting the application on aws
What am I planning to work on next? | Integrate Mysql & mock login page | Design Seat booking UI | integrated flight schedule page on frontend and backend | updated departure information for 4 hr | Added Airport and Flight details | Merge backend and frontend for airport employee | Fix issues in flight schedule page & login page | NA
What tasks are blocked waiting on another team member? | NA | None | NA | NA | NA | NA | NA | NA
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Week #1: Communication - others choice of design